CA Info No. 2, February 2005

Comprehensive Assessment of Water Management in Agriculture

- progress in brief-

The CA Info provides an update on the CA-related events and partnerships, as well as news on the CA synthesis process, projects and publications. If you have any problem opening files, please contact the Mala Ranawake at the CA secretariat (m.ranawake@cgiar.org).

More information can be found at: http://www.IWMI.cgiar.org/assessment/index.asp

Table of Contents:

1. CA outreach events & meeting opportunities

2. CA partnerships

3. CA technical assessment-synthesis process

3.1. CA synthesis process

3.2. The timeline for the production of the assessment

3.3. Teams and calendar of events

4. CA projects - news

4.1. Resources

4.2. News

5. CA publication news

5.1. Resources

5.2. News

6. Important information/events in Feb-April for the CA

# 1. CA outreach events & opportunities

The following table outlines the main events where the CA or research supported by the CA have been presented. In addition, meetings of projects or working groups closely related to the work being developed by the CA and coordinated by members of the CA steering committee are indicated.

| Dates 2005 | Events | Importance for CA | Participant | Relevant Outputs & Links |
| --- | --- | --- | --- | --- |
| End Jan | CGIAR System Priorities Technical Meetings, Rome, Italy. | Link CA into CGIAR priorities | David Molden | Enhance knowledge of the CA in the CGIAR system |
| 26-28 /1 | International workshop African Water Laws: Plural Legislative Frameworks for Rural Water Management in Africa, South Africa | Input into policy/institution chapter and preparation of an assessment book on African water laws | Barbara Van Koppen, member of poverty/gender working group | Website of the workshop Statement of the workshop All presentations/papers will be posted on CA website |
| 31/1 – 3/2 | IAASTD meeting , Bangkok, Thailand | Global design team, will work on the different issues-including water | David Molden, Lead of CA Charlotte de Fraiture, scenarios team | Website of IAASTD CA main contributor to water component for the IAASTD |
| 31/1 – 4/2 | FAO/Netherlands conference “water for food and ecosystems”, The Hague, the Netherlands | Core issues of the CA will be debated at the conference. No specific side event by the CA. | Domitille Vallee, CA synthesis team. Laurence Smith UK (CA sponsored project on Fishery) | -Link to conference site -Water for food and ecosystems bulletin produced by IISD – http://www.iisd.ca/sd/wfe -Case study (CA project): Assessing the impacts of irrigation on fisheries – results from Lao PDR (Huay Thouat) and Sri Lanka (Kirindi Oya) case on website |
| 2/2 | Meeting at Wageningen University, Wageningen, the Netherlands. | Raise awareness on the CA, and get involvement of Wageningen researchers | Domitille Vallee, Synthesis team Bas Bouman, steering committee Flip Wester, Wageningen, Basin chapter | Interest of Wageningen researchers to get involved in CA and univ to develop cooperation with IWMI. Suggestion to develop a climate change chapter in CA –part 2 scenarios. More: Wester, Flip [Flip.Wester@wur.nl] |
| 3/2 | Meeting on Gender/poverty integration in the CA, The Hague | Hosted by Gina Castillo at Novib meeting to set gender/poverty working groups, define working plan | Domitille Vallee, synthesis team More: D.vallee@cgiar.org | Gender and water alliance and Both ends to get involved in the preparation of a gender/poverty chapter (currently working on a joint proposal with CA to Novib to support their work) |
| 16/2 | Ecosystem chapter writing team meeting (some of the LAs only) | Discuss the ecosystem chapter contributing authors and chapter messages | Malin Falkenmark, Line Gordon, Michael Moore-coordinators, with online communication with Tabeth Chiuta, Max Finlayson | See chapter progress in section 3 more: Michael Moore [m.moore@telia.com] |
| 19/2 | Policy chapter writing team meeting (some of the lead authors only) | Discuss the policy chapter contributing authors and chapter messages | Doug Merrey, Eiman Karar, Claudia Ringler with online communication with Paul van Hofwegen | See chapter progress in section 3 More: Doug Merrey (d.merrey@cgiar.org) |
| 23-24/2 | Groundwater workshop | Prepare an assessment book on groundwater governance and prepare the CA chapter | David Molden, Chapter team at IWMI (Tushar Shah, Mark Giordano, Karen Villvoth) + 20 external participants | Agenda of the workshop More: Mark Giordano, m.giordano@cgiar.org) As a follow up of the workshop an online discussion will be organized around the papers presented. |

# 2. CA partnerships

This section summarizes new partnerships that are being developed by and for the CA.

| Featured Partner | Meetings | Interest of the Partner | Role for the CA |
| --- | --- | --- | --- |
| Gender and Water Alliance www.genderandwateralliance.org | Meeting at Novib, the Netherlands, 3/2/05 | Strengthen its “agricultural water component” | Network of experts working on Water and Gender around the world. |
| Both Ends www.bothends.org | Side event at FAO conference & Meeting at Novib, the Netherlands, 3/2/05 | Learn from the CA gender working group what are the critical issues to be addressed in water management particularly at basin level | Link to Networks of NGOs working on environment, water, agriculture & fishery |
| WUR Wageningen www.wu.nl | Meeting at Wageningen, the Netherlands, 2/2/05 | Ensure that their research on water/food/ecosystems is considered in the CA | Pool of scientific expertise in the CA priority areas Opportunity for joint efforts |
| International Network for Water and Ecosystem in Paddy Fields (INWEPF) www.maff.go.jp/inwepf/index.htm | Side event at FAO conference | Bring the issue of multi-functionality of agricultural water into the CA | Potential contributor for the rice chapter as well as the chapter on impacts of irrigation |

# 3. CA technical assessment – synthesis process

## 3.1. CA synthesis teams and process

The CA synthesis phase is built on a workforce of around 200 people in 13 teams or expert groups (graph 3) coordinated by the CA secretariat in charge of the synthesis and coordination. For more information, please see Ca website.

## 3.2. The timeline for the production of the assessment is the following

The critical steps for the preparation of the assessment are described in the annotated detailed timeline.

## 3.3. Teams and calendar of events

The following table follows the content of the main synthesis book The Comprehensive Assessment and indicates the progress of the different chapters. The writing chapter teams (CLAs and LAs) are now set for most of the chapters. The contributing authors have also been identified and will be involved in online discussions soon.

The CA calendar of events intends to bring together events that are substantively relevant to he CA or organized by the CA (CA projects, CA chapter workshops). It is not exhaustive and will benefit from your regular inputs. It will be posted on the CA website.

| Issues | CLAs | LAs | CLA & LA Meetings | Timeline | Draft Outline | Upcoming Events |
| --- | --- | --- | --- | --- | --- | --- |
| Integration | David Molden Domitille Vallee Lisa Schipper |  |  | Overview 2005-2006 | TBD | Workshop CLAs 8-10/4/2005 Workshop CLAs & LAs: 26-28/9/2005 |
| Part 1 |  |  |  |  |  |  |
| Ground water | Tushaar Shah, (IWMI- India) | Jacob Burke, Karen Villvoth | 21-23/2/05 | GW timeline | GW draft messages | Workshop CLA, Las, 21-23/2/05 Online discussion after Workshop |
| Ecosystem/ Environment | Malin Falkenmark (SIWI-Sweden) | Line Gordon Max Finlayson Tabeth Chiuta Max Finlayson | 1/2/05, Stockolm Sweden & online | Ecosystem timeline | Eco draft messages | -lA meeting 1/2/2005 -First online discussion: 21/2 to 3/2005 -Workshop CLA, LAs, 6-8/6/2005 |
| Irrigation Impact | Jean Marc Faures (FAO) | Hugh Turral & others TBD | online; D. Molden & J.M. Faures met early 2/2005 | TBD | See II outline prepared in 3/2004 | -Workshop CLA, LAs, 8-10/6/2005 |
| Rainwater harvesting/ rainfed agriculture | Suhas Wani (ICRISAT) | Theib Oweis Johan Rockström | online; D. Molden & Theib Oweis met early February 2005 | TBD | see rain outline prepared in 3/2004 | -Workshop CLA, Las, 10-12/4/2005 (linked to CA book preparation) |
| Low quality water | Manzoor Qadir (ICARDA/IWMI) | Being finalized | Not yet; | TBD | TBD | -Workshop CLA, Las, 16-19/4/2005 (linked to land deg work) |
| Water productivity | Theib Oweis (ICARDA) | Being finalized | Not yet; D. Molden meeting with Theib Oweis early February 2005 | TBD | See WP outline prepared in 3/2004 | -Workshop CLA, Las, 10-12/4/2005 (linked to CA rainfed workshop & CP Karkhe basin water productivity WK) |
| Basins | François Molle (IWMI, IRD) | Flip Wester, Philip Hirsch | Online discussion; Meeting to be planned | TBD | See Bas-outline prepared in 3/2004 | - CA basin session at east African Conference (7-9/3/2005); -1st online discussion: March 2005 - presentation at Stockholm conf (8/2005); -session at historian conference (12/2005) - Large workshop on basin development in early 2006 (link to CA project) |
| Land degradation | Deborah Bossio (IWMI) | William Critchley Bancy Mati, TBD | -Online; met with D. Molden & D. Vallee on 17/2/05 | Land deg timeline | See LD outline chapter | -Workshop CLA, Las, 16-19/4/2005 (linked to low quality water wk) |
| Rice | Bas Bouman | Tuong TBD | -online | TBD | See rice outline | -workshop linked to INWEPF Workshop on Paddy, Water, Environment, Japan, 7-9/9 |
| Policy/ institutions | Doug Merrey (IWMI-SA) Eiman Karar (south Africa) | Paul Van Hofgewen Claudia Ringler | -D. molden Meeting with Doug Merrey early 2/2005 -LAs + online: 9/2/2005 | TBD | See PI outline prepared in 2/2005 | -Workshop CLAs, LAs 2-4/6/2005 (linked to low quality water wk) |
| fisheries | Patrick Dugan (world fish center) | Chris Bene, Robin welcome, v.v. Sunugan | TBD | TBD | available | -workshop CLA-LAS TBD -interesting inputs to come from “ International conference on land-water interface management for solving agriculture-fisheries-aquaculture conflicts in coastal zone, bac lieu, Vietnam”. |
| Poverty & gender | Gina Castillo (Novid) | Being finalized | Meeting 3/2 in The Hague | TBD | TBD | -Workshop CLA, Las, 30/5 to 1/6/2005 |
| Part 2 |  |  |  |  |  |  |
| Scenarios | Mark Rosegrant (IFPRI) | Mark Rosegrant, Charlotte de Fraiture, Johan Rockström | Meeting 8/12/2004, Stockolm (D. Molden, M. Rosegrant & J. Rockström). | Scenarios ideas & Workplan draft | List of questions for other chapters to be prepared | -CLA & LAs: 10-11/4/05 -CLA, LAs & contributors at IAASTD scenario meeting: 05/2005 |
| Expert groups |  |  |  |  | List of questions for other chapters to be prepared |  |
| Health expert group | CA secretariat | Flemming Konradsen & others | Potential CLA & LAs identified and contacted | contribution depending on other chapters | Initiated | Experts participating in relevant workshops as contributors |
| Gender expert group | Being decided Under the coordination of Gina Castillo (Novid) | Barbara van Koppen & others | Meeting 3/2 in The Hague | contribution depending on other chapters | TBD | Contribution to other chapters |
| (Climate change) | Saskia Werners (Wageningen University) |  | Meeting in 02/2005 between Frank Rijsberman & Saskia Werners | TBD | TBD | Offer by Wageningen University, will build upon work of Dialogue on water & climate |

# 4. CA projects- news

## 4.1. Resources

See the list of ongoing projects  supported by the CA. Details about projects.

## 4.2. News

The following are the latest reports and materials received at the CA secretariat that are currently being reviewed.

| Project Partners | Materials & Reports Received by the CA Secretariat | Status | CA Chapter |
| --- | --- | --- | --- |
| FAO with Mexican consultants | Literature review of irrigation impacts in Mexico, Central and South America; database and report | Available | Irrigation impacts |
| University of Chile; IADIZA in Mendoza, Argentina; University of Michigan | A Comparative Study of Modern Irrigation Water Systems and Rural Poverty in the Limari Basin, Chile and the Tunuyan Basin, Argentina: Institutional and Socio-Economic Aspects – final report | Summary available | Irrigation impacts; poverty |
| IWMI; IFPRI; Natural Resources Institute (NRI); Global Water Partnership (GWP); Faculty of Law and the Institute of Resources Assessment, University of Dar-es-Salaam, Tanzania | International workshop African Water Laws: Plural Legislative Frameworks for Rural Water Management in Africa, South Africa http://www.nri.org/waterlaw/AWLworkshop/call.htm | Proceedings & statement available | Policy/ institution |
| International Center for Biosaline Agriculture (ICBA), Dubai, UAE | Harnessing Salty Water to Enhance Sustainable Livelihoods of the Rural Poor in Four Countries in West Asia and North Africa: Egypt, Jordan, Syria and Tunisia (Project completion report – synthesis report- policy brief). Also available bibliography on saline water resources and their use in agricultural production commissioned from Cornell University Library. | Under review (your feedback on the policy brief are welcome) | Low quality water |
| CA secretariat | Health related issues in irrigated agriculture – a literature review, by Leyla Ozay, 2004. | Document available at CA secretariat | Irrigation impacts environment |

# 5. CA publication news

## 5.1. Resources

See the updated bibliography of the CA

Glossary: A dictionary of unit of measurements online

## 5.2. News

Latest publications that have been released or are about to be released produced by the CA secretariat, or by CA or network partners

| Series | Title of publication | contact | PDF | CA chapter |
| --- | --- | --- | --- | --- |
| Paper | Spatial and temporal variability of water productivity in the Syr Darya basin, Central Asia, Iskandar Abdullaev & David Molden in Water Resources Research, Vol. 40, WO8SO2, 2004. | David Molden |  | Water productivity |
| Water Policy briefing IWMI/GWP Issue 12 | Integrating fisheries into irrigation planning and management, (based on a CA supported research) | GWP resource center | available | fishery |
| Water Policy briefing IWMI/GWP Issue 13 | Reducing poverty through integrated management of groundwater and surface water | GWP resource center | available | Poverty & gender |
| IAC report | Realizing the promise and potential of African agriculture, science and technology strategies for improving agricultural productivity and food security in Africa, Interacademy Council | IAC secretariat secretariat@iac.knaw.nl www.interacademycouncil.net |  | Water productivity Policies/institutions Land degradation |
| MAP technical reports series 158 | L’eau des mediterraneens: situations et perspectives, Plan Bleu by Jean Margat, PNUE/PAM, 2004 (in French only) | Plan bleu | www.planbleu.org see publications section |  |
| Agricultural economics research Institute (LEI), The Hague report 3-04-12 | Water as an economic good in irrigated agriculture: theory and practice, By P.J.G.J Hellegers and C.J. Perry | Publicatie.lei@wur.nl |  | Policy/ institution Irrigation impacts |
| Paper | David Groenfeldt, Multifunctionality of agricultural water: looking beyond food production and ecosystem services, prepared for the FAO/Netherlands conference, February 2005 | DGroenfeldt@aol.com |  | Impacts environment |

# 6. Important information/events in February-April for the CA

Events: The table below indicates a list of events where CA partners will make a presentation on behalf of the CA, as well as specific events organized by the CA.

| Dates | Events | Importance for CA | Contact or Participant | Relevant Outputs & Links |
| --- | --- | --- | --- | --- |
| End February 2005 |  |  |  |  |
| 20-23 | Workshop “groundwater governance” | CA event / to prepare the CA book on groundwater governance & the inputs for the chapter of the CA synthesis | Groundwater book & chapter team | Book and chapter outline and content |
| 23-25 | International Conference on Integrated Assessment of Water Resources and Global Change: A north-south analysis". 23-25 in Bonn | Organized by the Global Water System Project (GWSP), Tentative title of presentation: 'Linking river basin studies to the global context: an application of the WATERSIM model' | Charlotte de Fraiture, CA scenarios team, Claudia Ringler, policy chapter Deborah Bossio, land deg chapters | Presentations |
| 21-23 | Project meeting of the assessment of Bhavani river | CA project “Water Resources, Livelihood Security and Stakeholder Initiatives in a River Basin Context-the Bhavani river” | Linköping University | More on the project |
| 23-26 | IWMI-TATA partners meeting, Anand, India Focus: India’s Water Economy: Bracing Up for a Turbulent Future | India is an important agriculture water user. The IWMI TATA program offers an opportunity for outreach to policy makers. | Tushar Shah, groundwater chapter CLA & David Molden | Link to IWMI TATA website |
| March 2005 |  |  |  |  |
| 1-3 | International Conference on Effective Land-Water Interface Management for Solving Agriculture-Fishery-Aquaculture Conflicts in Coastal Zones, Bac Lieu, Vietnam | CA sponsored event Organised by WorldFish Center, IRRI, IWMI, People’s Committee of Bac Lieu Province, Can Tho University, Vietnam | Dr. Chu Thai Hoanh, IWMI, cthoanh@cgiar.org Dr. To Phuc Tuong, IRRI, t.tuong@cgair.org | More details Registration form Content for Assessment Book |
| 7-9 | The East African Integrated River Basin Management Conference Morogoro, Tanzania | CA sponsored event & 1 CA session on basins bring together river basin professionals and researchers to critically discuss the tools of IWRM applied at the basin level | Sokoine University-Soil-Water Management Group: swmrg@suanet.ac.tz Henry F. Mahoo: hmahoo@suanet.ac.tz Leader of one CA project | More details Session on basin comparisons Link to project page of Sokoine University |
| 14-16 | Developing policy for more effective management of water resources for community based irrigation in Ethiopia, Addis Ababa, Ethiopia | CA project workshop “Community-based Irrigation Management in Ethiopia : Strategies to Enhance Human Health, Livestock and Crop Production, and Natural Resource Management” | International livestock research institute ILRI, Addis Ababa, Ethiopia Don Peden d.peden@cgiar.org | program link to project page on ca website more on ILRI website |
| April 2005 |  |  |  |  |
| 8-10 | CA CLAs workshop (face-to-face and online) | CA event First synthesis workshop with all the CA coordinating lead authors; with online workshop to involve the whole writing teams | David Molden, CA lead IWMI | Agreement on assessment process, outputs, team and consultation working process |
| 10-12 | CA chapter Workshop on rainfed agriculture | CA event CA synthesis process; this workshop will probably be organized with CA workshop on water productivity | Sunas Wani, ICRISAT | Content for chapter, Content for assessment book |
| 10-12 | Workshop on water productivity (CA & CP) | CA event this workshop will be linked with CA workshop on rainfed agriculture | Theib Oweis, ICARDA | Content for chapter, Content for assessment book |
| TBD | Final Workshop of Chile /Argentina irrigation impact project | CA project “A Comparative Study of Modern Irrigation Water Systems and Rural Poverty in the Limarí Basin, Chile and the Tunuyán Basin, Argentina” | Alejandro Leon, project leader aleon-a@uchile.cl | Link to project |