Overview of Procedures

for the Synthesis Phase of the Comprehensive Assessment

This document provides an overview of the actions required to build the Comprehensive Assessment.  The process requires time-bound interactions among diverse teams to produce key outputs, then interactions across teams to harmonize the assessment.

Ca Participants:  The task of each team is share knowledge and experience, decide on key assessment messages, and produce written material for the assessment.  Much of the work will be done virtually, and funds permitting, each team will have one face-to-face meeting to debate The CA will be composed of:

- 10 Chapter teams–drawn from diverse location, experience, gender. composed of a coordinating lead author (CLA), supported by 2 to 3 lead authors (LA), and several contributing authors (8-10). It informs and virtually consults a broader chapter network of interested individuals.

- 4 Cross-cutting issues teams to ensure that critical questions on poverty and gender, health, environment and governance are incorporated in the various chapters, and be responsible for synthesizing information into cross-cutting chapters.   Members of these teams will participate in the chapter teams to facilitate this integration.

- A Scenario development team – has the task of developing and analyzing scenarios for the assessment in consultation with the lead authors of the other chapters.  It will have a smaller core team, but use the chapter and cross-cutting themes in the consultative process.

- A Review team – independent review team of about 20 reviewers drawn from different disciplines and experience to review individual chapters and full synthesis headed by a review panel.

- CA Secretariat – will facilitate the process, ensure linkages between chapters, and liaise with the CA Steering Committee.  The secretariat will provide support in identifying people for chapters, setting up a virtual discussion web space, organizing literature reviews, organizing workshops, preparing briefing material, and facilitating the review process.

- CA consultation network: This network group gathers people the CA wants to target (policy makers, practitioners, implementers, researchers, users). It includes those who showed interest in participating in the CA (call for nominations) plus others who have shown interest or would be interested.

## Tasks and responsibilities within chapter teams:

Responsibilities:

- Coordinating Lead Author (CLA) – takes ultimate responsibility for the chapter, prepares a workplan, prepares together with lead authors key messages, chapter drafts, responds to reviews, and prepares final draft of chapter.  CLAs will be required to attend meetings on cross cutting and synthesis issues.  Together with lead authors they should communicate regularly with the secretariat, stimulate discussions and flag contentious issues for broader discussion.

- Lead Authors – have the responsibility for drafting part of the chapter as agreed by the lead author group.  They may attend synthesis meetings in place of CLA.

- Contributing Authors – contribute material to the text, provide critical feedback to the chapter, attend face-to-face workshop, and agree on chapter outline.

- Network participants and Authors – participate in on-line discussions of chapter and submit relevant material.

Summary of Tasks for Lead Authors The objective if to manage the CA preparation as a learning process where active exchange is sought. A summary of the tasks of the CLAs and LA team is as follow: 1. Before end of January- Start discussion with other lead authors to: - Identify chapter teams chapter network - Define a work-plan with a timeline 2005-2006 & budget (in particular set dates for face to face workshop and online discussions or conferences for chapter preparation) 2. Before end of March: - Prepare expanded number of questions the chapter should address (giving attention to questions from co-sponsors and cross cutting groups) - Prepare first draft key messages for online discussion 3. Before end July: - Expand key messages into a draft chapter outline and hold online discussion - Hold a face-to-face workshop to gain consensus on the chapter outline, key messages and supporting evidence - Write chapter 4. From February to September: - Contribute to the scenario development exercise with a long term look on the chapter findings. - Contribute to work of cross-cutting issues teams 5. From September 2005 to February 2006: - Revise chapter after each review – in September 2005, in January 2006. - Provide critical elements for the overview for policy makers

Integrating Cross-Cutting Issues And Scenarios Development: Cross cutting issues cover poverty and gender, ecosystems, water productivity, climate change, health and governance and require special treatment.

There will be cross-cutting chapters on poverty and gender; ecosystems, water productivity and policies and institutions having their own teams, and running much like other chapters with a few additions listed below.  Cross cutting teams will:

- Propose critical questions to be covered by other assessment chapter, in addition to the specific cross cutting chapter.

- Participate in important chapter preparations and workshops when relevant for the issue

- Contribute to chapters – providing written material, tables, graphs or other key pieces of evidences

- Incorporate material from other chapters in the cross cutting chapter.

- Review across chapters to ensure good integration of critical cross-cutting issues.

Gender, climate change, and health will not have their own dedicated chapters.  But to ensure integration, special gender and health working groups will be formed.  Their tasks are to bring up these issues and communicate them to various chapter teams.

The concept of water productivity enters into several chapters.  It will be presented in the conceptual framework, included in various chapters, then synthesized into its own chapter.

To develop and analyze scenarios, a small working group will be formed that works in consultation with CLAs and LAs from other chapters.  The scenario working group will develop or use qualitatitve story lines (it is likely to use the same story line approach as IAASTD), then provide qualitative and quantitative analysis of the scenario.  The scenarios group will develop their chapter slightly later than the other groups in order to receive information from the chapters.  The scenario group will communicate closely with chapter lead authors to communicate the type of information needed from chapters, and to hear what chapter teams would like from the scenarios.

Ca Secretariat Support And Communication: The CA secretariat coordinates the overall communication and outreach activities and facilitates the process of putting together the assessment.  The CA secretariat will be responsible for:

- Developing and maintaining a dynamic website used by all the CA participants and linked to other websites.

- Providing a regular email update on the progress of the CA (built on exchanges with steering committee, project leaders, and chapter’s coordinators).

- A working web space to connect the CA steering committee members where all the “working documents” are made available

- Where appropriate, development of issues briefs in consultation with lead authors

In development of chapters, the secretariat will:

- Provide logistic and advisory support for workshops and on-line discussions.

- Facilitate the development and presentation of content, especially in harmonizing across chapter

- Help to organize workshops

- Assist in communication with chapter teams

The secretariat requires close support, especially from the CLAs.  CLAs and LAs will be expected to:

- Represent the CA at various meetings.

- Identify times where they will need to use available CA tools & outputs (webpage, E-forum, E-list, type of publication, briefs.

- Support the networking and dissemination effort of the secretariat through their specific networks.

## Timeline:

The detailed timeline of tasks of each team is shown in the following tables.

| Dates | Activity | Content |
| --- | --- | --- |
| Assessment process preparation |  |  |
| 08.2004 | Launching CA synthesis | Stockholm 2004. Call for nominations of interested participants |
| 11.2004-01.2005 | assessment process preparation | Lead Authors and CA secretariat: set up globally diverse teams to prepare individual chapters of the technical assessment (10 chapter teams, 4 cross-cutting teams and 1 scenario team). CLAs and CA secretariat identify lead authors, contributing authors and broader network, and communicate this to team members. The CLAs should prepare a timeline of events for their chapter in consultation with the secretariat. |
| 01-03.2005 | Organize individual chapter writing, consultation and outreach process | Compile assessment questions for each chapter drawn from (CLA, LA, CAs): The co-sponsors and clients of the Assessment: the Ramsar convention, FAO, and CGIAR Cross cutting chapter working groups – poverty/gender, ecosystems, health, governance Issues that the CLAs and LAs identify Cross-cutting teams define critical questions to be addressed by other chapters |
| 04.2005 | Assessment and Process Workshop | For coordinating lead authors (CLA workshop, Aleppo, April, 2005): Ensure common understanding of overall process and chapter inputs Gain insights on working in diverse teams Detailed work plan per chapter, draft outline and questions to projects Develop detailed chapter drafting procedures |

| Dates | Activity | Content |
| --- | --- | --- |
| First Draft of Chapters writing, with participation, consultation and information sharing |  |  |
| 02-07.2005 | Chapter writing through intensive consultation process | Use the following procedure to prepare a first draft of the chapter: Draft key messages and provide supporting evidence dealing referring to assessment questions (CLA and LA) On line discussion of key messages and evidence (team) Flag the most contentious issues and possibly develop issues brief on these First draft of detailed chapter outline followed by on-line discussion. Contributors asked to provide material – tables, references, written material Face to face meeting resulting in an agreed chapter outline. CLA and LA develop first chapter draft and submit to secretariat |
| 03-06.2005 | More about the chapter Workshops | The workshop gathers the lead & contributing authors and if relevant 1 from the cross-cutting issues teams. The workshop will result in an agreed upon chapter outline. Key elements of the workshop include: Review of assessment questions, draft outline, supporting evidence Brief presentations of relevant evidence drawn from CA research and other experience Discussions on the most contentious issues Consensus on key messages, or where there is not consensus identification of why views differ Consensus on chapter outline, including tables, graphs and evidence to be presented. Identification of key response options to be presented in the chapter Identification of issues to be dealt with by scenarios group. |
| 07.2005 | 1st chapter draft | Draft chapter with messages, and evidences submitted to CA secretariat (CLA and LA) |
| 07-09.2005 | 1st chapter review | Review panel review assigns individual chapters to reviewers to check scientific validity of assessment; CA Secretariat invites review from extended network Key chapter messages discussed at various appropriate meetings to gain feedback. Opportunities for testing the messages of the chapter in face to face meetings may arise in high level events and conferences organized throughout 2005. |

| Dates | Activity | Content |
| --- | --- | --- |
| Synthesis across chapters and second draft |  |  |
| 26-28.09.2005 (tentative dates) | Synthesis Workshop, | Gather all the coordinating lead authors to Present key elements of their chapters, Check and harmonize across chapters, Ensure integration of cross-cutting issues Discuss story lines and scenarios Extract key elements for overview for policy makers |
| Mid-09.05 to 01.11.05 | Second draft preparation and 1st draft overview for policy makers | Chapter writing teams & cross cutting groups revise individual chapters (version 2) in consultation with contributing authors and network Scenarios team continues analysis based on results of synthesis workshop, and prepares 1st draft of scenarios chapter First draft of overview for policy makers prepared |
| 11-12.2005 | Second review | Review panel oversees second scientific review, paying attention to the structure of entire document Stakeholder consultations and review 1st review of scenarios and overview document |

| Dates | Activity | Content |
| --- | --- | --- |
| Publication and Special Report Preparation |  |  |
| 01 to mid-02.2006 | Final draft of chapters | Preparation of chapter final draft attending to reviewers and stakeholder comments Second draft of scenarios and overview Preparation of briefs for WWF |
| mid-02 to mid-03.2006 | Water Forum preparations | Second review of scenarios and overview Presentations at 3rd WWF for stakeholder consultation and final feedback Beginning of final approval process by co-sponsors, SC |
| mid-03 to mid-04.2006 | Preparation of Final Draft | Revisions based on final reviews, stakeholder consultations, and final approval process |
| 01.05.05 | Final approval | By cosponsors, review panel, SC |
| 05-07.2006 | Editing and publishing | Substantive and scientific editing (May to July 2006) Publishing and distributing overview at Stockholm meeting (August 2006) Publishing Assessment (August – September, 2006) |
| 08.2006 | Stockholm Water Week | Presentation of key findings |
| 10.2006 | Delivery | Delivery of Assessment |
| 09.2005-12.2006 | Preparation of Special Reports | Special report preparation - special reports proposed for Ramsar on wetlands and agriculture, South Asia, Sub-Saharan Africa |
| 05.2006-03.2007 | Continuing outreach and communication | Based on approved material, preparation of policy briefs, communication material, and presentation of results to various audiences. Normal outreach happens throughout the entire process. |

Working Outline

Comprehensive Assessment of Water Management for Agriculture

Page Length guidance: 875 words per page - half page graphs are equivalent to 450 words.  About 13 000 words for 15 pages, 17 500 for 20 pages.

Section 1: Setting the Scene

- Introduction [5 pp.] – This chapter will set the scene and introduce the context of the assessment.

- Conceptual Framework [20 pp.] – Outlines the approach of the CA and introduces key concepts that lie behind the assessment and integrate the document together.

- Benefits, Costs & Challenges of Managing Water for Agriculture [20 pp.] – Assesses trends, status and challenges of water management for agriculture, focusing on the positive and negative impacts of efforts to develop and manage water for agriculture, especially on poverty, food security, and  the environment.

Section 2: Thematic Chapters

These chapters will assess the trends, conditions, challenges and responses in management of the various water resources for agriculture.

- Rainfed Agriculture [20 pp.] – Explores potential of rainfed systems, including small-scale supplemental irrigation, for food production and improving livelihoods.

- Irrigation [20 pp.] – Critically evaluates past impacts of irrigation to identify options for improved development and management of irrigation.

- Groundwater [15 pp.] – Assesses groundwater and its governance, in particular in areas of overdraft, and in areas of high potential to increase food security and improve livelihoods.

- Low Quality Water [15 pp.] – Assesses the status and significance of use saline water, city wastes, and other low quality water, and options and consequence of its use.

- Fish [15 pp.] – Assesses the extent and value of capture fisheries and aquaculture, their roles in freshwater management, and significance in food and environmental security.

- Rice [15 pp.] – As rice plays an important role in use of water for food, this section critically evaluates its impacts on water resources, and explores ways for improved management in light of increasing competition.

- Land [15 pp.] – Assesses how land management influences productivity of water and its influence on overall water resources, and evaluates means to reverse trends of land and water degradation.

- Basins [20 pp.] – Assesses past trends of development and management of water in basins, their impacts, and future challenges for river basin management.

Section 3: cross-cutting issues

These chapters assess the trends, conditions, challenges and responses with respect to four cross-cutting issues, and will bring together views and perspectives relevant to these issues that emerge from the preceding chapters.

- Water Productivity [15 pp.] – Clarifies concepts of water productivity, identifies trends and conditions in the area, then assesses potential of various approaches to improve water productivity.

- Policies and Institutions [20 pp.] – Integrates across chapters and provides an assessment of past institutional processes and reforms to provide guidance on appropriate institutional arrangements and polices for the future under various contexts.

- Ecosystems [20 pp.] – Assesses the impact of developing and managing water for food on important ecosystems, and suggests means to co-manage water to balance food and environmental security.

- Poverty [20 pp.] – Assesses interactions of poverty and agricultural water management practices over the past 50 years, as well as current challenges, potential solutions and response options.

Section 4: Looking ahead

- Future Scenarios [40 pp.] – This section explores the consequences of future investments using scenario analysis.  It qualitatively and quantitatively analyzes impacts of near term investments over the next 25 and 50 years using a limited set of scenarios representing plausible futures to draw out policy relevant recommendations.

Section 5: Summary for Policymakers

XVII. Summary for Policymakers [30 pp.] – This overview synthesizes results over the entire assessment.  It will serve as a stand alone document written for policymakers.

Section 6: References & Information

- References

- Glossary

- Authors and Acknowledgements

- Index